## Feature Register
ID | Feature | Stage | Sprint | Epic | Version | Status
P1 | Monorepo foundation & tooling | 0-platform | S1 | E1 | 1.0 | Planned
P2 | DigitalOcean infrastructure & CI/CD | 0-platform | S1 | E1 | 1.0 | Planned
P3 | Database schema, migrations & type generation | 0-platform | S1-S2 | E2 | 1.0 | Planned
P4 | Object storage (Spaces) integration | 0-platform | S2 | E2 | 1.0 | Planned
P5 | Authentication - email/password + sessions | 0-platform | S2 | E3 | 1.0 | Planned
P6 | RBAC, route guards & audit log | 0-platform | S2 | E3 | 1.0 | Planned
P7 | Observability, hardening, backups & launch | 0-platform | S1,S6 | E8,E9 | 1.0 | Planned
W1 | Source registry & scheduler | 1-watch | S3 | E4 | 1.0 | Planned
W2 | RSS & news-API connectors | 1-watch | S3 | E4 | 1.0 | Planned
W3 | Social connectors (X/IG/FB/TikTok) | 1-watch | S3-S4 | E4 | 1.0 | Planned
W4 | Normalization, dedup & raw storage | 1-watch | S3 | E4 | 1.0 | Planned
W5 | Initial recent-window backfill | 1-watch | S3 | E4 | 1.0 | Planned
U1 | LLM provider abstraction & cost ledger | 2-understand | S4 | E5 | 1.0 | Planned
U2 | Article enrichment (score/issues/sentiment/summary/keywords) | 2-understand | S4 | E5 | 1.0 | Planned
U3 | Geocoding & incident mapping | 2-understand | S4 | E5 | 1.0 | Planned
U4 | Crisis snapshots & trends | 2-understand | S4 | E5 | 1.0 | Planned
U5 | Predictions, insights, actor & leadership analytics | 2-understand | S4-S5 | E5 | 1.0 | Planned
A1 | Dashboard read API & caching | 3-act | S2,S5 | E6 | 1.0 | Planned
A2 | Widget integration & live data | 3-act | S5 | E6 | 1.0 | Planned
A3 | Persisted dashboard layout | 3-act | S5 | E6 | 1.0 | Planned
A4 | AI assistant - copilot chat | 3-act | S5 | E7 | 1.0 | Planned
A5 | AI assistant - briefing, forecast & per-widget ask | 3-act | S5 | E7 | 1.0 | Planned
A6 | Real-time ticker, alerts & War Room | 3-act | S5-S6 | E8 | 1.0 | Planned

## Sprint Plan
Sprint | Window | Primary features | Milestone | Sprint goal / exit
S1 | Jun 1-12, 2026 | P1, P2, P3 (start), P7 (skeleton) | - | Monorepo + DO infra + CI/CD; local stack boots; web deploys to staging.
S2 | Jun 15-26, 2026 | P3 (finish), P4, P5, P6, A1 (initial) | M1: DB-backed dashboard | Real login + RBAC; dashboard renders from Postgres, not static JSON.
S3 | Jun 29-Jul 10, 2026 | W1, W2, W4, W5, W3 (spike) | - | Scheduled crawl ingests real Indonesian articles; raw to Spaces; dedup.
S4 | Jul 13-24, 2026 | U1, U2, U3, U4, W3 (cont.) | M2: live enrichment | Model-agnostic enrichment writes real data; cost tracked; provider switchable.
S5 | Jul 27-Aug 7, 2026 | U5, A1 (finish), A2, A3, A4, A5, A6 (start) | M3: feature-complete | All widgets on live data; assistant grounded on DB; layouts persist; realtime.
S6 | Aug 10-21, 2026 | A6 (finish), P7 (hardening/launch) | M4: production launch | Security review, load test, backups/DR, runbooks, UAT, prod cutover.

## WBS
Epic | Workstream | Scope
E1 | Foundation & DevOps | Monorepo, DO infra (Terraform), CI/CD, Docker Compose, observability skeleton.
E2 | Data Model & Storage | Alembic schema (source of truth), seed from static JSON, Kysely codegen, Spaces.
E3 | Auth & User Management | Email/password, sessions, RBAC (admin/analyst/viewer), audit log, admin seed.
E4 | Ingestion Pipeline | Celery + Beat, SourceConnector, RSS/news/social connectors, dedup, raw store.
E5 | AI Enrichment Pipeline | LiteLLM abstraction, scoring/geo/sentiment/predict, snapshots, cost ledger.
E6 | API/BFF & Frontend Integration | Read APIs from Postgres, TanStack Query, layouts, trend charts.
E7 | AI Assistant Productization | Port assistant to Python ai-api; chat/briefing/forecast/widget; proxy + fallback.
E8 | Real-time & Observability | NOTIFY->SSE ticker/alerts, OpenTelemetry, dashboards, freshness alerts.
E9 | Hardening, Security & Launch | Security review, load test, backups/DR, runbooks, UAT, cutover.

## Gantt
Epic | Workstream | S1 Jun 1-12 | S2 Jun 15-26 | S3 Jun 29-Jul 10 | S4 Jul 13-24 | S5 Jul 27-Aug 7 | S6 Aug 10-21
E1 | Foundation & DevOps | core | support |  |  |  | support
E2 | Data Model & Storage | support | core | support
E3 | Auth & User Management |  | core | support
E4 | Ingestion Pipeline |  |  | core | support
E5 | AI Enrichment Pipeline |  |  | support | core | support
E6 | API/BFF & Frontend Integration |  | support |  | support | core | support
E7 | AI Assistant Productization |  |  |  | support | core | support
E8 | Real-time & Observability | support |  |  |  | support | core
E9 | Hardening, Security & Launch | [5 empty] | core
| Milestone |  | M1 |  | M2 | M3 | M4
| Legend: | core | support | milestone

## Risk Register
ID | Risk | Severity | Mitigation
R1 | Social APIs (X/IG/FB/TikTok) can't monitor arbitrary accounts cheaply/legally | High | Connector abstraction; RSS+news first; paid aggregators per-platform with ToS/legal review + cost cap; social is incremental.
R2 | LLM enrichment cost scales with article volume | Med | Cheap model for scoring, strong for summaries; batch; daily budget guardrail; cost ledger.
R3 | Geocoding accuracy for Indonesian locales | Med | LLM NER + gazetteer reconcile; unmapped_count surfaced in UI.
R4 | Scraping / ToS legal exposure | Med | Prefer official APIs/RSS; legal review before aggregator use; respect robots/ToS.
R5 | Polyglot monorepo friction (TS + Python) | Low | Clear boundaries, generated contracts, Taskfile, docker-compose parity.
R6 | Scope creep into Settings / multi-tenant | Med | Explicit non-goals; defer to future phase.
R7 | 3-month timeline with 2-3 devs | Med | Social ingestion incremental; RSS+news+AI is the MVP spine; cut social platforms first if behind.

## Milestones
ID | Milestone | When | Target date
M1 | DB-backed dashboard (real auth + reads from Postgres) | End S2 | 2026-06-26
M2 | Live ingestion + AI enrichment writing real data | End S4 | 2026-07-24
M3 | Assistant + real-time on live data (feature-complete) | End S5 | 2026-08-07
M4 | Production launch | End S6 | 2026-08-21